## Presentations
category | task | start date | time allotted for task | end date | comment
All | date of event | 2016-09-27 | 1 | 2016-09-27
presentations | Final copy of presentation put on flash drive and sent to Lisa Howells morning of event | 2016-09-27 | 1 | 2016-09-27
presentations | final new grad presentations sent for approval | 2016-09-21 | 4 | 2016-09-25
presentations | executive presenter presentation added to powerpoint | 2016-09-21 | 1 | 2016-09-22 | Expected to receive on 20/09/2016.
presentations | new grad presentations returned for revisions | 2016-09-16 | 5 | 2016-09-21
presentations | NG informed of when and where they will need to stand to get their gift | 2016-09-22 | 1 | 2016-09-22
presentations | script delivered to presenters for practice | 2016-09-21 | 1 | 2016-09-22 | must be sent to Arlan
presentations | powerpoint sent to Fabienne and discipline leads for approval | 2016-09-12 | 7 | 2016-09-19 | Check that they have been sent off to DMs. 07/09/2016 Skeleton sent to DL
presentations | script submitted to discipline leads for approval | 2016-09-12 | 7 | 2016-09-19 | Done 16/09/2016.
presentations | draft new grad presentations for approval | 2016-09-19 | 4 | 2016-09-23 | 19/09/2016 sent to Fabienne. Check that they have been passed off to DMs.
presentations | new grad presentations written | 2016-09-12 | 7 | 2016-09-19 | Done 19/09/2016. 16/09/2016 Anna handed in first draft. 12/09/2016 currently outstanding with NG.
presentations | script for discipline leads, MC, safety moment written | 2016-09-07 | 5 | 2016-09-12 | Done 15/09/2016
presentations | executive presenter secured | 2016-09-07 | 2 | 2016-09-09 | Done 08/09/2016- Warren Linland
presentations | new grad presenter selected | 2016-09-07 | 2 | 2016-09-09 | Done 12/09/2016. 08/09/2016 KS will ask Melanie and Austin. 07/09/2016 With Fabienne
presentations | guidelines for new grad presentations written | 2016-09-07 | 2 | 2016-09-09 | Done 12/09/2016. to be done week of 12-16. will be sent to NG once we are informed officially who that will be.
presentations | do first round edits to ppt | 2016-09-09 | 1 | 2016-09-09 | Done. 08/09/2016 comments provided by KS in PDF. Updates will be done by EOD by Meghan.
presentations | thank-you email sent to DL for agreeing to present | 2016-09-08 | 1 | 2016-09-08 | Done 08/09/2016- sent by Carmen with the NG account
presentations | discipline leads agree to present | 2016-09-07 | 2 | 2016-09-09 | Done 08/09/2016. Arlan Brandt will do presentations. 07/09/2016 With Fabienne
Formulas:
start date = [end date, row below]
end date = [start date]
end date = [start date]+1

## Invites
category | task | start date | time allotted for task | end date | Comments
Invites | send invite list to Fabienne and DL | 2016-09-07 | 1 | 2016-09-07 | Done 07/09/2016 -left with Fabienne
Invites | send invite email to Fabienne and DL | 2016-09-07 | 1 | 2016-09-07 | Done 07/09/2016 -left with Fabienne
Invites | invite list and invite email approved by Fabienne and DL | 2016-09-07 | 2 | 2016-09-09 | Done 08/09/2016 left with Fabienne
Invites | invite list and email returned to NG Committee | 2016-09-09 | 1 | 2016-09-09 | Done 08/09/2016
Invites | invite list and email sent to Lisa Howells | 2016-09-09 | 1 | 2016-09-09 | Done 08/09/2016
Invites | CVent invite sent out | 2016-09-11 | 1 | 2016-09-11 | Done 12/09/2016. 08/09/2016 - currently outstanding with Lisa Howells. Awaiting Fabienne's final approval.
Invites | additions made as needed | 2016-09-11 | 9 | 2016-09-20 | Done.
Invites | RSVP received | 2016-09-11 | 9 | 2016-09-20 | Done. See "Reg Report - Sept 20" excel.
Invites | Follow-up sent to graduates declining to attend | 2016-09-21 | 1 | 2016-09-21 | Done.
Invites | Potluck adjustments made as needed | 2016-09-20 | 3 | 2016-09-23 | see "Potluck List" tab
Invites | Email sent to designation recipients | 2016-09-23 | 1 | 2016-09-23 | Do we need to do this?
All | date of event | 2016-09-27 | 1 | 2016-09-27
Formulas:
start date = [end date, row above]
start date = [end date, row above]+2
end date = [start date]
end date = [start date]+3

## Misc
category | task | start date | time allotted for task | end date | Comments
Misc | get cc from Fabienne | 2016-09-07 | 2 | 2016-09-09 | 07/09/2016 Fabienne will get us cc (discussed in meeting)
Misc | book room | 2016-09-09 | 1 | 2016-09-09 | Done 16/09/2016. Meeting setup with Lisa Howells to discuss the room on 15/09/2016. 09/09/2016 Jordan has left the PDF with Carmen and Meghan to be sent to Lisa Howells once we have the cc. everything else has been filled out and reviewed in meeting on 07/09/2016.
Misc | write human bingo | 2016-09-12 | 7 | 2016-09-20 | Done 14/09/2016.
MIsc | send potluck email | 2016-09-20 | 1 | 2016-09-20 | Done as people reply. See Potluck list tab.
Misc | send out human bingo for approval | 2016-09-21 | 1 | 2016-09-21 | Done 16/09/2016.
Misc | human bingo returned approved, changes made, printed | 2016-09-23 | 4 | 2016-09-27
Misc | procure "gifts" for NG | 2016-09-20 | 7 | 2016-09-27 | Done 20/09/2016. See email from Janice Hughes. Follow-up email sent on 12/09/2016. KS is looking into this (phone conversation on 08/09/2016 with Fabienne)
Misc | Get cue cards for potluck labels. Print? | 2016-09-22 | 4 | 2016-09-26
Misc | Get paper plates,, cutlery, etc. | 2016-09-22 | 4 | 2016-09-26 | Done 19/09/2016.
Misc | Touch base with Lisa Howells | 2016-09-26 | 1 | 2016-09-26
Misc | Make Kudos certificates | 2016-09-21 | 1 | 2016-09-21 | Done 21/09/2016.
Misc | Print Kudos certificates | 2016-09-27 | 1 | 2016-09-27 | can we get a thicker stock paper?
All | date of event | 2016-09-27 | 1 | 2016-09-27
OOO | Fabienne in Houston | 2016-09-12 | 7 | 2016-09-19
OOO | Jordan Away | 2016-09-12 | 14 | 2016-09-26
OOO | Carmen Away | 2016-09-19 | 8 | 2016-09-28
Formulas:
start date = [end date, row above]
start date = [end date]
end date = [start date]
end date = [end date, row below]

## Potluck List
Contributor | Email | Category | Description
Tom Chin | tom.chin@cenovus.com | Dessert
Lisa Qiu | Lisa.Qiu@cenovus.com
Helen Rignault | Helen.rignault@cenovus.com | Appetizer
Anthony Elder | anthony.elder@cenovus.com | Dessert | fruit tray

## Day-of Event Notes
A list of the graduates will be kept at the check-in desk with the nametags. A confirmed list of the attending recipients will be provided to Arlan before the presentation begins
Pens will need to be provided for the BINGO. Additinally, we will need two display racks to hold up the sheets so people can't miss them.Could use plate holderswith cardboard backing.
--> I have jars for the pens, will grab the actual pens from
People will be brining their potluck contributions to the 54 floor as they arrive
For the potluck I have:
40 plates
40 cutlery
40 napkins
38 cups
They will set out water jugs at potluck
Lisa will print nametags. Ensure she also prints them for the people who have not responded in case they do decide to come.
Do we need to have all the presenters sitting at a table for easy access? What about New Grads?