## over all timeline
category | task | start date | time allotted for task | end date | comment | f
All | date of event | 2021-08-12 | 1 | 2021-08-12
Daily Check-in | check-in with mentor | 2021-08-11 | 1 | 2021-08-11 | (a) what has been accomplished, (b) what will you be working on, (c ) what hurdles are you facing
Presentation | Presentation dry run (feedback from education team) | 2021-08-11 | 1 | 2021-08-11
Daily Check-in | check-in with mentor | 2021-08-10 | 1 | 2021-08-10 | (a) what has been accomplished, (b) what will you be working on, (c ) what hurdles are you facing
Presentation | Hopin tech dry run | 2021-08-10 | 1 | 2021-08-10
Project Deployment | Deploy to an app template | 2021-08-11 | 1 | 2021-08-10 | bonus. Otherwise this can be a catch-up day
presentation | write/make presentation | 2021-08-10 | 1 | 2021-08-10
presentation | collect baseline idea maybe by recording video of what the #hairstylist tag on instagram looks like right now | 2021-08-10 | 1 | 2021-08-10
post MVP: project development | post MVP: test different layer count and hyperparameters to find optimal solution | 2021-08-10 | 1 | 2021-08-10
post MVP: project development | After MVP: pre-processing: data set 1 -- expand data set with shearing, flipping ,etc. | 2021-08-10 | 1 | 2021-08-10 | may need to move around if model trains badly
post MVP: project development | try other models | 2021-08-10 | 1 | 2021-08-10 | https://www
Daily Check-in | check-in with mentor | 2021-08-09 | 1 | 2021-08-09 | (a) what has been accomplished, (b) what will you be working on, (c ) what hurdles are you facing
MVP DONE | MVP DONE | 2021-08-09 | 1 | 2021-08-09
personal | cohort chat | 2021-08-09 | 1 | 2021-08-09
making model | define and train latent space portion of model | 2021-08-07 | 2 | 2021-08-09 | https://www | analyticsvidhya
Daily Check-in | check-in with mentor | 2021-08-08 | 1 | 2021-08-08 | (a) what has been accomplished, (b) what will you be working on, (c ) what hurdles are you facing
Daily Check-in | check-in with mentor | 2021-08-07 | 1 | 2021-08-07 | (a) what has been accomplished, (b) what will you be working on, (c ) what hurdles are you facing
Gather Data | data set 2: ensure that data fits with goal final | 2021-08-07 | 1 | 2021-08-07
project development | Data cleaning: data set 2 -- get pictures to be the same size | 2021-08-07 | 2 | 2021-08-07
Daily Check-in | check-in with mentor | 2021-08-06 | 1 | 2021-08-06 | (a) what has been accomplished, (b) what will you be working on, (c ) what hurdles are you facing
Gather Data | data set 1: ensure that data fits with goal final | 2021-08-05 | 1 | 2021-08-06
Gather Data | data set 2: get photos from hairstylist websites | 2021-08-04 | 1 | 2021-08-06
Job Hunt Stuff | git repo setup - add Git link to linkedin | 2021-07-30 | 7 | 2021-08-06
Job Hunt Stuff | git repo setup - add Git link to employer services resume | 2021-07-30 | 7 | 2021-08-06
Job Hunt Stuff | update resume for employment services | 2021-07-30 | 7 | 2021-08-06
Daily Check-in | check-in with mentor | 2021-08-05 | 1 | 2021-08-05 | (a) what has been accomplished, (b) what will you be working on, (c ) what hurdles are you facing
Project Description | finalize project description in document for employers | 2021-08-05 | 1 | 2021-08-05 | I believe it is sent out on the Friday, so have done on Thursday
Daily Check-in | check-in with mentor | 2021-08-04 | 1 | 2021-08-04 | (a) what has been accomplished, (b) what will you be working on, (c ) what hurdles are you facing
making model | define and train encoder and decoder portion of model | 2021-08-01 | 3 | 2021-08-04 | https://www | analyticsvidhya
Daily Check-in | check-in with mentor | 2021-08-03 | 1 | 2021-08-03 | (a) what has been accomplished, (b) what will you be working on, (c ) what hurdles are you facing
personal | cohort chat | 2021-08-03 | 1 | 2021-08-03
Project Workflow | Deliverable: project milestones document | 2021-08-03 | 1 | 2021-08-03 | just use this and have it cleaned up?
personal | Katie and Kevin Visit | 2021-08-02 | 2 | 2021-08-03
Daily Check-in | check-in with mentor | 2021-08-02 | 1 | 2021-08-02 | (a) what has been accomplished, (b) what will you be working on, (c ) what hurdles are you facing
Project Setup | train test split and save the files into separate spaces to save time | 2021-08-05 | 1 | 2021-08-01
Daily Check-in | check-in with mentor | 2021-08-01 | 1 | 2021-08-01 | (a) what has been accomplished, (b) what will you be working on, (c ) what hurdles are you facing
personal | Canmore | 2021-07-31 | 1 | 2021-08-01
project development | Data cleaning: data set 1 -- get pictures to be the same size | 2021-07-30 | 2 | 2021-08-01
Gather Data | data set 1: save images into folder with labels | 2021-07-31 | 1 | 2021-07-31
Daily Check-in | check-in with mentor | 2021-07-31 | 1 | 2021-07-31 | (a) what has been accomplished, (b) what will you be working on, (c ) what hurdles are you facing
Gather Data | data set 1: use curly hair pictures from that kaggle data set | 2021-07-30 | 1 | 2021-07-31
Gather Data | data set 1: set up folder to hold data | 2021-07-30 | 1 | 2021-07-31
Gather Data | data set 2: ensure that data fits with goal prelim | 2021-07-30 | 1 | 2021-07-30
Reseach | based on article runs, determine if plan needs to be updated | 2021-07-30 | 1 | 2021-07-30
Gather Data | data set 1: ensure that data fits with goal prelim | 2021-07-31 | 1 | 2021-07-30
Project Setup | Git repo setup - Create a repo on GitHub and make public. | 2021-07-30 | 1 | 2021-07-30
Reseach | run provided articles the same way I do walk throughs | 2021-07-30 | 1 | 2021-07-30
Daily Check-in | check-in with mentor | 2021-07-30 | 1 | 2021-07-30 | (a) what has been accomplished, (b) what will you be working on, (c ) what hurdles are you facing
Reseach | set up plan | 2021-07-29 | 1 | 2021-07-29
Daily Check-in | check-in with mentor | 2021-07-29 | 1 | 2021-07-29 | done 2021-07-28
Project Description | Provide initial, high level description of the project | 2021-07-29 | 1 | 2021-07-29 | done 2021-07-28
Reseach | read provided articles | 2021-07-29 | 1 | 2021-07-29 | done 2021-07-28
Formulas:
start date = [end date]
start date = [end date, row above]

## Invites (hidden)
category | task | start date | time allotted for task | end date | Comments
Invites | send invite list to Fabienne and DL | 2016-09-07 | 1 | 2016-09-07 | Done 07/09/2016 -left with Fabienne
Invites | send invite email to Fabienne and DL | 2016-09-07 | 1 | 2016-09-07 | Done 07/09/2016 -left with Fabienne
Invites | invite list and invite email approved by Fabienne and DL | 2016-09-07 | 2 | 2016-09-09 | Done 08/09/2016 left with Fabienne
Invites | invite list and email returned to NG Committee | 2016-09-09 | 1 | 2016-09-09 | Done 08/09/2016
Invites | invite list and email sent to Lisa Howells | 2016-09-09 | 1 | 2016-09-09 | Done 08/09/2016
Invites | CVent invite sent out | 2016-09-11 | 1 | 2016-09-11 | Done 12/09/2016. 08/09/2016 - currently outstanding with Lisa Howells. Awaiting Fabienne's final approval.
Invites | additions made as needed | 2016-09-11 | 9 | 2016-09-20 | Done.
Invites | RSVP received | 2016-09-11 | 9 | 2016-09-20 | Done. See "Reg Report - Sept 20" excel.
Invites | Follow-up sent to graduates declining to attend | 2016-09-21 | 1 | 2016-09-21 | Done.
Invites | Potluck adjustments made as needed | 2016-09-20 | 3 | 2016-09-23 | see "Potluck List" tab
Invites | Email sent to designation recipients | 2016-09-23 | 1 | 2016-09-23 | Do we need to do this?
All | date of event | 2016-09-27 | 1 | 2016-09-27
Formulas:
start date = [end date, row above]
start date = [end date, row above]+2
end date = [start date]
end date = [start date]+3

## Misc (hidden)
category | task | start date | time allotted for task | end date | Comments
Misc | get cc from Fabienne | 2016-09-07 | 2 | 2016-09-09 | 07/09/2016 Fabienne will get us cc (discussed in meeting)
Misc | book room | 2016-09-09 | 1 | 2016-09-09 | Done 16/09/2016. Meeting setup with Lisa Howells to discuss the room on 15/09/2016. 09/09/2016 Jordan has left the PDF with Carmen and Meghan to be sent to Lisa Howells once we have the cc. everything else has been filled out and reviewed in meeting on 07/09/2016.
Misc | write human bingo | 2016-09-12 | 7 | 2016-09-20 | Done 14/09/2016.
MIsc | send potluck email | 2016-09-20 | 1 | 2016-09-20 | Done as people reply. See Potluck list tab.
Misc | send out human bingo for approval | 2016-09-21 | 1 | 2016-09-21 | Done 16/09/2016.
Misc | human bingo returned approved, changes made, printed | 2016-09-23 | 4 | 2016-09-27
Misc | procure "gifts" for NG | 2016-09-20 | 7 | 2016-09-27 | Done 20/09/2016. See email from Janice Hughes. Follow-up email sent on 12/09/2016. KS is looking into this (phone conversation on 08/09/2016 with Fabienne)
Misc | Get cue cards for potluck labels. Print? | 2016-09-22 | 4 | 2016-09-26
Misc | Get paper plates,, cutlery, etc. | 2016-09-22 | 4 | 2016-09-26 | Done 19/09/2016.
Misc | Touch base with Lisa Howells | 2016-09-26 | 1 | 2016-09-26
Misc | Make Kudos certificates | 2016-09-21 | 1 | 2016-09-21 | Done 21/09/2016.
Misc | Print Kudos certificates | 2016-09-27 | 1 | 2016-09-27 | can we get a thicker stock paper?
All | date of event | 2016-09-27 | 1 | 2016-09-27
OOO | Fabienne in Houston | 2016-09-12 | 7 | 2016-09-19
OOO | Jordan Away | 2016-09-12 | 14 | 2016-09-26
OOO | Carmen Away | 2016-09-19 | 8 | 2016-09-28
Formulas:
start date = [end date, row above]
start date = [end date]
end date = [start date]
end date = [end date, row below]

## Pre Processing Timeline
category | task | start date | time allotted for task | end date | comment
Gather Data | data set 2: ensure that data fits with goal final | 2021-08-05 | 1 | 2021-08-07
Gather Data | data set 1: ensure that data fits with goal final | 2021-08-05 | 1 | 2021-08-06
Gather Data | data set 2: get photos from hairstylist websites | 2021-08-04 | 1 | 2021-08-06
project development | Data cleaning: data set 1 -- get pictures to be the same size | 2021-07-31 | 2 | 2021-08-01 |  | analyticsvidhya | com/blog/2021/01/querying-similar-images-with-tensorflow/
Project Setup | train test split and save the files into separate spaces to save time | 2021-07-31 | 1 | 2021-08-01
Gather Data | data set 1: use curly hair pictures from that kaggle data set | 2021-07-29 | 4 | 2021-07-31
Gather Data | data set 1: set up folder to hold data | 2021-07-29 | 4 | 2021-07-31
Gather Data | data set 1: save images into folder with labels | #REF! | #REF! | 2021-07-31
Gather Data | data set 2: ensure that data fits with goal prelim | 2021-08-04 | 1 | 2021-07-30
Reseach | based on article runs, determine if plan needs to be updated | 2021-07-30 | 1 | 2021-07-30
Reseach | run provided articles the same way I do walk throughs | 2021-07-30 | 1 | 2021-07-30
Gather Data | data set 1: ensure that data fits with goal prelim | 2021-07-30 | 1 | 2021-07-30
Reseach | set up plan | 2021-07-29 | 1 | 2021-07-29 | done 2021-07-29
Reseach | read provided articles | 2021-07-29 | 1 | 2021-07-29 | done 2021-07-28
project development | Data cleaning: data set 2 -- get pictures to be the same size |  | 2 | 2021-08-07

## Invite List
Person | Email
Dad
Matt

## Presentation Ideas
- get school photo from Dad